## Product Backlog
Product backlog

		Total Estimation	78
Item Number	Group	Description	Story Points	Status	Responsible	Priority	Sprint	Description
1	Risk Identification	As a user I want to enter, edit, and delete / risks. A risk is characterized by a description, / a location, a type, a date, and a time.	2	C	E,G,T	H	1
2	Risk Identification	As a user I want to view all the risks of a / given type.	1	C	E,G,T	H	1
3	Risk Identification	As a user I want to enter and view related / data using selection lists (and not numbers)	1	C	E,G,T	H	1
4	Risk Identification	As a user I want to search for risks by type, / description, time, or location.	5	O	E,G,T	M	1
5	Risk Identification	As a user I wan to enter different intervals / (time or date) for any given risk	5	O	E,G,T	M	1
6	Risk Identification	As a user I want to view the locations on a / map.	10	O	E,G,T	L	1
7	Risk Identification	As a user I want to paginate the list of / risks.	3	C	E,G,T	H	1
8	Risk Identification	As a user I want to make sure only / authorized people can edit risks.	4	O	E,G,T	L	1
9	Risk Identification	As a user I want to attach a document / to a risk.	6	C	E,G,T	L	1
10	Risk Identification	As a user I want to define the types of / risks.	1	C	E,G,T	H	1
11	Risk Identification	As a user I want to define the locations / using a geographical name.	7	O	E,G,T	L	1
12	Risk Identification	As a user I want to define the locations / clicking on a map and defining a radius.	10	O	E,G,T	L	1
13	Risk Assessment	As a user I want that the access to the application is limited. Moreover I want to be able to register and login.	2	O	E,G,T	L	2
14	Risk Assessment	As a user I want to assign a probability and an impact to a risk during a certain period.	7	O	E,G,T	H	2
15	Risk Assessment	As a user I want to see the risk matrix	3	O	E,G,T	H	2
16	Risk Assessment	As a user I want to assign two types of impact: human, infrastructure. Note the these they will have different scales.	5	O	E,G,T	H	2
17	Risk Assessment	As a user I want to define my own types of impact	2	O	E,G,T	M	2
18	Risk Assessment	As a user I want to choose which types of impact to use during the assessment	4	O	E,G,T	M	2

## Sprints Specification
Sprints Specification

Sprint Number	Start Date	Duration (Days)	End Date	Allocated Points	Status	Code Name
1	Jul 29, 13	4	Aug 2, 13	#NAME?
2	Aug 5, 13	4	Aug 9, 13	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?
			Dec 30, 99	#NAME?

## Sprint 1
			Progress
Sprint Detail

Sprint Number	1
Start Date	29/07/13
Duration	4
Allocated Points	39
Average Point Burndown	9.75

		Day	0	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28
		Date	07/29/13	30/07	31/07	01/08	02/08	03/08	04/08	05/08	06/08	07/08	08/08	09/08	10/08	11/08	12/08	13/08	14/08	15/08	16/08	17/08	18/08	19/08	20/08	21/08	22/08	23/08	24/08	25/08	26/08
		Remaining Days	4	3	2	1	0	-1	-2	-3	-4	-5	-6	-7	-8	-9	-10	-11	-12	-13	-14	-15	-16	-17	-18	-19	-20	-21	-22	-23	-24
Insert Task ID, the rest is computed		Ideal burn-down >	39	29	20	10	0	-10	-20	-29	-39	-49	-59	-68	-78	-88	-98	-107	-117	-127	-137	-146	-156	-166	-176	-185	-195	-205	-215	-224	-234
Task ID	Responsible	Actual burn-down >	39	32	23	22	6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
1	E,G,T	As a user I want to enter, edit, and delete risks. A risk is characterized by a description, a location, a type, a date, and a time.	2	0	0	0	0
2	E,G,T	As a user I want to view all the risks of a given type.	1	1	0	0	0
3	E,G,T	As a user I want to enter and view related data using selection lists (and not numbers)	1	0	0	0	0
10	E,G,T	As a user I want to define the types of risks.	1	0	0	0	0
7	E,G,T	As a user I want to paginate the list of risks.	3	0	0	0	0
4	E,G,T	As a user I want to search for risks by type, description, time, or location.	5	5	3	2	0
9	E,G,T	As a user I want to attach a document to a risk.	6	6	0	0	0
6	E,G,T	As a user I want to view the locations on a map.	10	10	10	10	5
12	E,G,T	As a user I want to define the locations clicking on a map and defining a radius.	10	10	10	10	1
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A

## Sprint 2
			Progress
Sprint Detail

Sprint Number	2
Start Date	05/08/13
Duration	4
Allocated Points	23
Average Point Burndown	5.75

		Day	0	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28
		Date	08/05/13	06/08	07/08	08/08	09/08	10/08	11/08	12/08	13/08	14/08	15/08	16/08	17/08	18/08	19/08	20/08	21/08	22/08	23/08	24/08	25/08	26/08	27/08	28/08	29/08	30/08	31/08	01/09	02/09
		Remaining Days	4	3	2	1	0	-1	-2	-3	-4	-5	-6	-7	-8	-9	-10	-11	-12	-13	-14	-15	-16	-17	-18	-19	-20	-21	-22	-23	-24
Insert Task ID, the rest is computed		Ideal burn-down >	23	17	12	6	0	-6	-12	-17	-23	-29	-35	-40	-46	-52	-58	-63	-69	-75	-81	-86	-92	-98	-104	-109	-115	-121	-127	-132	-138
Task ID	Responsible	Actual burn-down >	23	21	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
16	E,G,T	As a user I want to assign two types of impact: human, infrastructure. Note the these they will have different scales.	5	4
14	E,G,T	As a user I want to assign a probability and an impact to a risk during a certain period.	7	6
15	E,G,T	As a user I want to see the risk matrix	3	3
17	E,G,T	As a user I want to define my own types of impact	2	2
18	E,G,T	As a user I want to choose which types of impact to use during the assessment	4	4
13	E,G,T	As a user I want that the access to the application is limited. Moreover I want to be able to register and login.	2	2
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A
	#N/A	#N/A	#N/A

## Actual Speed
Time Log and Actual Speed

Item ID	Date	From Time	To Time	Hours	Burndown	Burndown Speed	Comment	Other Info
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!
				00:00		#DIV/0!

## Resource Load
Resource Load

Filter

(empty)	Sprint
Responsible	(empty)	Total Result
(empty)
Total Result